## Current Opportunities
HS2 Current Contract Opportunities
11/01/2021 For external publication
This table provides information on all key contracts currently being procured by HS2 Ltd, as well as awarded contracts over £1m, with supplier contact emails provided to help users enquire about subcontract opportunities.
Cells highlighted in yellow are changes from the previous version
Please register on our e-sourcing portal, Bravo Solution
HS2 Reference No. | Category | Description | Procurement Route | Framework Title | Status | Contract Award Date | Tenderers / Awarded Suppliers (including contact details where appropriate) | Link to Contract Notice | Indicative Budget | Value category (highest-lowest)
HS2 Project_917 | Rolling Stock | HS2 rolling stock procurement | https://www.gov.uk/government/publications/hs2-rolling-stock-procurement | N/A | ITT in evaluation | Q2 2021 | ITT shortlist: • Alstom Transport - tim.ward@alstomgroup.com • Bombardier Transportation UK Ltd and Hitachi Rail Europe - nupur.agarwal@rail.bombardier.com / Ella.Adamo@hitachirail-eu.com • Construcciones y Auxiliar de Ferrocarriles (CAF) - HS2Opportunities@caf.net • Patentes Talgo S.L.U. - Suppliers@talgo.com • Siemens Mobility - erdil.houssein.ext@siemens.com | http://ted.europa.eu/udl?uri=TED:NOTICE:151144-2017:TEXT:EN:HTML | >£1bn | £500m - £3bn
HS2_1040 | Construction | Euston Over Site Development Master Development Partner |  | N/A | Awarded | Q1 2018 | Lendlease Europe Holdings Limited - Richard.Payne@lendlease.com Robert.Heasman@lendlease.com | http://ted.europa.eu/udl?uri=TED:NOTICE:137452-2017:TEXT:EN:HTML | >£1bn | £500m - £3bn
Phase One: MWCC2556/N1 | Construction | Civil Engineering: Long Itchington Wood Tunnel South Portal to Delta Junction and Birmingham Spur (N1) |  | N/A | Awarded | Q3 2017 | BBV JV (Balfour Beatty Group Limited, VINCI Construction UK Limited, VINCI Construction Terrassement) Procurement contact: HS2BBVenquiries@balfourbeattyvinci.com Innovation contact: Dan Fawcett - MyContribution@balfourbeattyvinci.com | http://ted.europa.eu/udl?uri=TED:NOTICE:343503-2015:TEXT:EN:HTML&src=0 | £900m - £1.5bn | £500m - £3bn
Phase One: MWCC2557/N2 | Construction | Civil Engineering: Delta Junction to West Coast Main Line Tie -In (N2) |  | N/A | Awarded | Q3 2017 | BBV JV (Balfour Beatty Group Limited, VINCI Construction UK Limited, VINCI Construction Terrassement) Procurement contact: HS2BBVenquiries@balfourbeattyvinci.com Innovation contact: Dan Fawcett - MyContribution@balfourbeattyvinci.com | http://ted.europa.eu/udl?uri=TED:NOTICE:343503-2015:TEXT:EN:HTML&src=0 | £900m - £1.5bn | £500m - £3bn
Phase One: MWCC2552/S2 | Construction | Civil Engineering: Northolt Tunnels (S2) | https://www.competefor.com/scsjv/ | N/A | Awarded | Q3 2017 | SCS JV (Skanska Construction (UK) Limited, Costain Limited, STRABAG AG) Procurement contact: procurement@scsrailways.co.uk Innovation contact: Harrison.ohara@scsrailways.co.uk | http://ted.europa.eu/udl?uri=TED:NOTICE:343503-2015:TEXT:EN:HTML&src=0 | £850m - £1.4bn | £500m - £3bn
Phase One: MWCC2553/C1 | Construction | Civil Engineering: Chiltern Tunnels and Colne Valley Viaduct (C1) |  | N/A | Awarded | Q3 2017 | Align JV (Bouygues Travaux Publics, VolkerFitzpatrick Limited, Sir Robert McAlpine Limited) Procurement contact: contact@align-jv.co.uk Innovation contact: Simon Poulter - s.poulter@alignjv.com | http://ted.europa.eu/udl?uri=TED:NOTICE:343503-2015:TEXT:EN:HTML&src=0 | £800m - £1.3bn | £500m - £3bn
Phase One: MWCC2554/C2 | Construction | Civil Engineering: North Portal of Chiltern Tunnels To Brackley (C2) | https://www.competefor.com/ekfb/ | N/A | Awarded | Q3 2017 | EKFB JV (Eiffage Genie Civil, Kier Infrastructure and Overseas Limited, Ferrovial Agroman and BAM Nuttall) Procurement contact: Supplychainenquiries@ekfb.com Innovation contact: Laurent.Vincont@eiffagekier-hs2.team | http://ted.europa.eu/udl?uri=TED:NOTICE:343503-2015:TEXT:EN:HTML&src=0 | £800m - £1.3bn | £500m - £3bn
Phase One: MWCC2551/S1 | Construction | Civil Engineering: Euston Tunnels & Approaches (S1) | https://www.competefor.com/scsjv/ | N/A | Awarded | Q3 2017 | SCS JV (Skanska Construction (UK) Limited, Costain Limited, STRABAG AG) Procurement contact: procurement@scsrailways.co.uk Innovation contact: Harrison.ohara@scsrailways.co.uk | http://ted.europa.eu/udl?uri=TED:NOTICE:343503-2015:TEXT:EN:HTML&src=0 | £600m - £900m | £500m - £3bn
Phase One: MWCC2555/C3 | Construction | Civil Engineering: Brackley to South Portal of Long Itchington Wood Tunnel (C3) | https://www.competefor.com/ekfb/ | N/A | Awarded | Q3 2017 | EKFB JV (Eiffage Genie Civil, Kier Infrastructure and Overseas Limited, Ferrovial Agroman and BAM Nuttall) Procurement contact: Supplychainenquiries@ekfb.com Innovation contact: Laurent.Vincont@eiffagekier-hs2.team | http://ted.europa.eu/udl?uri=TED:NOTICE:343503-2015:TEXT:EN:HTML&src=0 | £600m - £900m | £500m - £3bn
CPC2163 - P1 CPC Lot 1 | Construction | HS2 Phase One Stations: Construction Partner (Euston) |  | N/A | Awarded | Q1 2019 | Mace Limited and Dragados S.A. Procurement@macedragados.com | http://ted.europa.eu/udl?uri=TED:NOTICE:332984-2017:TEXT:EN:HTML | £1.65bn | £500m - £3bn
CPC2164 - P1 CPC Lot 2 | Construction | HS2 Phase One Stations: Construction Partner Contracts (Old Oak Common) |  | N/A | Awarded | Q3 2019 | Balfour Beatty Group Ltd, VINCI Construction UK Ltd, VINCI Construction Grands Projets SAS and SYSTRA Ltd Manish Taylor - BBVS.supplierenquiries@balfourbeatty.com | http://ted.europa.eu/udl?uri=TED:NOTICE:332984-2017:TEXT:EN:HTML | £1.3bn | £500m - £3bn
Phase One: C1000_2191 | Construction | HS2 Phase One Stations: Design & Build (Birmingham Curzon Street) | Negotiated OJEU | N/A | ITT | Q2 2021 | ITT Shortlist: - BAM Ferrovial JV - pmchugh@bam.co.uk - Laing O'Rourke Construction Limited - Bradley Heaps BHeaps@laingorourke.com - Mace Limited and Dragados S.A. - Bid.Team@macegroup.com | https://ted.europa.eu/udl?uri=TED:NOTICE:37860-2020:TEXT:EN:HTML | £570m | £500m - £3bn
HS2_TBC | Railway Systems | Control, Command & Signalling (CCS) and Traffic Management | Negotiated OJEU | N/A | PQQ | Q4 2022 | TBC | https://ted.europa.eu/udl?uri=TED:NOTICE:225813-2020:TEXT:EN:HTML&src=0 | £540m | £500m - £3bn
HS2_TBC | Railway Systems | HV Power System | Negotiated OJEU | N/A | PQQ | Q3 2022 | TBC | https://ted.europa.eu/udl?uri=TED:NOTICE:378281-2020:TEXT:EN:HTML&src=0 | £500m | £250 - 500m
HS2_TBC | Construction | Phase One Stations — Framework Agreement for Lifts and Escalators | Negotiated OJEU | N/A | ITT | Q3 2021 | TBC | https://ted.europa.eu/udl?uri=TED:NOTICE:187644-2020:TEXT:EN:HTML | £465m | £250 - 500m
HS2_TBC | Railway Systems | Track Installation (Phase One, Lot 1 Urban) | Negotiated OJEU | N/A | ITT | Q2 2022 | BBVT JV (Balfour Beatty Group, ETF, TSO) Colas Rail Ferrovial Construction / BAM Nuttall JV Rhomberg Sersa / Strabag JV | https://ted.europa.eu/udl?uri=TED:NOTICE:209541-2020:TEXT:EN:HTML | £400m | £250 - 500m
HS2_TBC | Railway Systems | Track Installation (Phase One, Lot 2 Central) | Negotiated OJEU | N/A | ITT | Q2 2022 | BBVT JV (Balfour Beatty Group, ETF, TSO) Colas Rail Ferrovial Construction / BAM Nuttall JV Rhomberg Sersa / Strabag JV | https://ted.europa.eu/udl?uri=TED:NOTICE:209541-2020:TEXT:EN:HTML | £400m | £250 - 500m
HS2_TBC | Railway Systems | Track Installation (Phase One, Lot 3 North) | Negotiated OJEU | N/A | ITT | Q2 2022 | BBVT JV (Balfour Beatty Group, ETF, TSO) Colas Rail Ferrovial Construction / BAM Nuttall JV | https://ted.europa.eu/udl?uri=TED:NOTICE:209541-2020:TEXT:EN:HTML | £400m | £250 - 500m
HS2_TBC | Railway Systems | Track Installation (Phase 2a, Lot 4) | Negotiated OJEU | N/A | ITT | Q2 2022 | BBVT JV (Balfour Beatty Group, ETF, TSO) Colas Rail Ferrovial Construction / BAM Nuttall JV Rhomberg Sersa / Strabag JV | https://ted.europa.eu/udl?uri=TED:NOTICE:209541-2020:TEXT:EN:HTML | £400m | £250 - 500m
HS2_TBC | Railway Systems | Tunnel and Lineside Mechanical & Electrical (M&E) | Negotiated OJEU | N/A | ITT | Q2 2022 | Alstom Transport UK BBB JV (Balfour Beatty Group & NG Bailey) Costain Group | https://ted.europa.eu/udl?uri=TED:NOTICE:305313-2020:TEXT:EN:HTML&src=0 | £350m | £250 - 500m
HS2_TBC | Railway Systems | Operational Telecommunication and Security Systems | Negotiated OJEU | N/A | PQQ | Q3 2022 | TBC | https://ted.europa.eu/udl?uri=TED:NOTICE:290781-2020:TEXT:EN:HTML | £300m | £250 - 500m
Phase One: EWC12101 | Construction | Enabling Works South |  | N/A | Awarded | Q4 2016 | CS JV (Costain Limited, Skanska Construction UK Limited) Procurement contact: supplier.enabling@costain-skanska-jv.co.uk Innovation contact: Shaun.Sheppard@csjv.co.uk | http://ted.europa.eu/udl?uri=TED:NOTICE:93208-2015:TEXT:EN:HTML&src=0 | £300m | £250 - 500m
Phase One: EWC12102 | Construction | Enabling Works Central |  | N/A | Awarded | Q4 2016 | Fusion JV (Morgan Sindall Construction and Infrastructure Limited, BAM Nuttall Limited, Ferrovial Agroman (UK) Limited) Procurement contact: alan.harris@fusion-jv.com Innovation contact: sam.hewlings@fusion-jv.com | http://ted.europa.eu/udl?uri=TED:NOTICE:93208-2015:TEXT:EN:HTML&src=0 | £300m | £250 - 500m
Phase One: EWC12103 | Construction | Enabling Works North |  | N/A | Awarded | Q4 2016 | LM JV (Laing O’Rourke Construction Limited, J. Murphy & Sons Limited) Procurement contact: Catherine Kelly catherine.kelly@lm-jv.com Innovation contact: Stephen Hinds shinds@lm-jv.com | http://ted.europa.eu/udl?uri=TED:NOTICE:93208-2015:TEXT:EN:HTML&src=0 | £300m | £250 - 500m
Phase Two: C1231; C1232; C1233 | Construction | Phase Two Professional Services Consultants - Civils design and environmental services |  | N/A | Awarded | Q1 2017 | Lot 1 • JV - Mott MacDonald Limited with WSP (UK) Limited - James.Montgomery@mottmac.com Lot 2 • JV - AECOM Limited with Capita Property and Infrastructure Limited & Ingenieria y Economia del Transporte, SA (INECO) - sajjad.akbar@aecom.com Lot 3 • Ove Arup and Partners International Ltd - Nigel.Hailey@arup.com | http://ted.europa.eu/udl?uri=TED:NOTICE:106018-2016:TEXT:EN:HTML&src=0 | £280-350m | £250 - 500m
Phase One: Ref 369 | Construction | Engineering Delivery Partner (EDP) |  | N/A | Awarded | Q1 2016 | CH2M Hill United Kingdom, Atkins Limited and SENER Engineering and Systems Ltd - hs2edp@ch2m.com | http://ted.europa.eu/udl?uri=TED:NOTICE:174639-2015:TEXT:EN:HTML&src=0 | £250m - £350m | £250 - 500m
HS2_TBC | Railway Systems | Overhead Catenary System (OCS) | Negotiated OJEU | N/A | PQQ | Q2 2022 | TBC | https://ted.europa.eu/udl?uri=TED:NOTICE:309373-2020:TEXT:EN:HTML&src=0 | £200m | £100 - 250m
C1186 | Railway Systems | Pre-cast Slab Track System (open route) - design, manufacture and supply |  | N/A | Awarded | Q3 2020 | Porr Bau GMBH, Aggregate Industries UK Ltd | http://ted.europa.eu/TED/notice/udl?uri=TED:NOTICE:359252-2017:TEXT:EN:HTML&WT.mc_id=RSS-Feed&WT.rss_f=Transport+and+Related+Services&WT.rss_a=359252-2017&WT.rss_ev=a | £200m | £100 - 250m
C1000_2824 & C1000_2823 | Corporate | Commercial Delivery and Controls Framework | Negotiated OJEU | N/A | Awarded | Q3 2020 | Lot 1: Programme Controls Atkins - michael.bond@atkinsglobal.com Lot 2: Commercial Management Gleeds - corporate_bidding@gleeds.co.uk | https://ted.europa.eu/udl?uri=TED:NOTICE:558450-2018:TEXT:EN:HTML&tabId=1 | £197.9m | £100 - 250m
Phase Two: C977 | Construction | Phase Two Development Partner |  | N/A | Awarded | Q4 2016 | Bechtel Limited - cbmcmona@bechtel.com | http://ted.europa.eu/udl?uri=TED:NOTICE:106022-2016:TEXT:EN:HTML&src=0&tabId=1 | £130-170m | £100 - 250m
B1032 | Railway Systems | Track: Switches & Crossings |  | N/A | PQQ | Q2 2022 | TBC | https://ted.europa.eu/udl?uri=TED:NOTICE:615812-2020:TEXT:EN:HTML | £122m | £100 - 250m
1SN01 | Construction | Phase One Stations Professional Services Design Contracts (London Euston Station) |  | N/A | Awarded | Q1 2018 | Ove Arup & Partners International Limited - John Turzynski (rail@arup.com) | http://ted.europa.eu/udl?uri=TED:NOTICE:137921-2017:TEXT:EN:HTML&src=0 | £87-98m | £50 - 100m
project_912 | Corporate | Neutral Vendor - Temporary Interim and Permanent Staff Recruitment | Further Competition | N/A | Awarded | Q4 2017 | Comensura | TBC | £58.7m | £50 - 100m
Package Order 2 | Corporate | Service Tasks |  | N/A | Awarded | Q2 2018 | EDP JV | TBC | £57.2m | £50 - 100m
1SN02 | Construction | Phase One Stations Professional Services Design Contracts (London Old Oak Common Station) |  | N/A | Awarded | Q1 2018 | WSP UK Limited - ian.howard@wspgroup.com | http://ted.europa.eu/udl?uri=TED:NOTICE:137921-2017:TEXT:EN:HTML&src=0 | £47-70m | £50 - 100m
B1028 | Construction | Framework Agreement for Stations Building Systems |  | N/A | PQQ | Q1 2022 | TBC | https://ted.europa.eu/udl?uri=TED:NOTICE:603240-2020:TEXT:EN:HTML | £47m | £10 - 50m
Phase Two: C862 | Construction | Railway Systems Design Services Framework |  | N/A | Awarded | Q4 2015 | Parsons Brinckerhoff Ltd (now WSP) Ian.Bleasdale@pbworld.com WSP - Adrian.Tooth@wsp.com, Chris.Hayter@wsp.com | http://ted.europa.eu/udl?uri=TED:NOTICE:450521-2015:TEXT:EN:HTML&src=0 | TBC | £10 - 50m
Phase Two: C863 | Construction | Site Access, Land Referencing and Landowner Engagement Framework: -Work Package (Phase 2a - West Midlands to Crewe) |  | N/A | Awarded | Q4 2015 | Mouchel Limited, Arup, AECOM, WSP nick.crowther@mouchel.com | http://ted.europa.eu/udl?uri=TED:NOTICE:450521-2015:TEXT:EN:HTML&src=0 | TBC | £10 - 50m
Package Order 1 | Corporate | WFP Headcount (Secondments) |  | N/A | Awarded | Q2 2018 | EDP JV | TBC | £36m | £10 - 50m
HS2_TBC | Construction | Procurement of routewide provision of Specialist Security Services |  | N/A | Awarded | Q4 2017 | Control Risks – dale.smith@controlrisks.com | http://ted.europa.eu/udl?uri=TED:NOTICE:22145-2017:TEXT:EN:HTML | £32m-42m | £10 - 50m
project_625 | Corporate | Specialist Security Services (SSS) | OJEU - Negotiated | N/A | Awarded | Q4 2017 | Control Risks Group Limited | TBC | £32.9m | £10 - 50m
HS2 Project_1488 | Railway Systems | Cross Passage Doors |  | N/A | Awarded | Q3 2020 | Booth Industries | N/A | £36m | £10 - 50m
2507 | Construction | Enabling Civils Works Package 2 (ECW2) | Further Competition | CCS Construction Works and Associated Services (CWAS) | ITT | Q2 2021 | TBC |  | £50m | £10 - 50m
1711 | Corporate | IT External Strategic Support Services (ITESSS) | Further Competition | CCS Technology Services 2 | ITT in evaluation | Q1 2021 | TBC |  | £24.8m | £10 - 50m
HS2_1652 | Corporate | IT Service Support Management and IT Infrastructure Support and Management Partners | Further Competition | CCS Technology Services 2 | Awarded | Q1 2020 | Lot 1 - Littlefish (UK) Ltd Lot 2 - MCSA Group Limited | TBC | £24.4m | £10 - 50m
1710 | Corporate | Property Management Services | Further Competition | CCS Estates Professional Services (RM3816) | ITT in evaluation | Q1 2021 | TBC |  | £22.5m | £10 - 50m
| Corporate | Rail Systems Support Contract |  |  | Awarded | Q3 2017 | WSP UK Limited |  | £20.6m | £10 - 50m
1755 | Corporate | Software Asset Management as a Service (SAMaaS) | Further Competition | CCS Technology Services 2 | Awarded | Q3 2020 | Bytes Software Services |  | £19.5m | £10 - 50m
1SN04 | Construction | Phase One Stations Professional Services Design Contracts (Birmingham Curzon Street Station) |  | N/A | Awarded | Q1 2018 | WSP UK Limited - ian.howard@wspgroup.com | http://ted.europa.eu/udl?uri=TED:NOTICE:137921-2017:TEXT:EN:HTML&src=0 | £18-30m | £10 - 50m
WP3 | Corporate | Acquisitions and Advice - Leeds Leg Central | Further Competition | N/A | Awarded | Q3 2017 | Valuation Office Agency | TBC | £18.4m | £10 - 50m
project_832 | Corporate | Property Management - Countrywide Package Order 17 - LSH | OJEU - Negotiated | N/A | Awarded | Q4 2014 | Lambert Smith Hampton Group Limited | TBC | £17.1m | £10 - 50m
WP4 | Corporate | Acquisitions and Advice - Leeds Leg North | Further Competition | N/A | Awarded | Q3 2017 | Carter Jonas | TBC | £14.6m | £10 - 50m
1SN03 | Construction | Phase One Stations Professional Services Design Contracts (Birmingham Interchange Station) |  | N/A | Awarded | Q1 2018 | Ove Arup & Partners International Limited - Andrew Lloyd (rail@arup.com) | http://ted.europa.eu/udl?uri=TED:NOTICE:137921-2017:TEXT:EN:HTML&src=0 | £13-23m | £10 - 50m
project_776 | Corporate | Total Facilities Management Service | Further Competition | N/A | Awarded | Q2 2018 | Interserve Plc | TBC | £12.4m | £10 - 50m
2169 | Corporate | Organisation Transformation Support | Further Competition | CCS Management Consultancy 2 Framework | ITT in evaluation | Q2 2021 | TBC | N/A | £12m | £10 - 50m
project_832 | Corporate | Legal, Construction Infrastructure |  | N/A | Awarded | Q1 2015 | Herbert Smith Freehills LLP | TBC | £11.1m | £10 - 50m
WP2 | Corporate | Acquisitions and Advice - Leeds Leg South | Further Competition | N/A | Awarded | Q3 2017 | Carter Jonas | TBC | £10.4m | £10 - 50m
HS2_1694 | Corporate | Long-term Editorial, Design and Visual Services | Direct Award under a Framework Agreement | NEPRO (NEPO) | Awarded | Q1 2019 | Bloom Procurement Services Limited | https://www.contractsfinder.service.gov.uk/Notice/09b5ca5d-611b-4da6-ba56-db0609264285 | £9.8m | £1 - 10m
1836 | Corporate | Technical Advisor Services for Rolling Stock and Railway Systems Integration | Further Competition | CCS Management Consultancy Framework (Lot 7 - Infrastructure) | ITT in evaluation | Q1 2021 | TBC | TBC | £8.5m | £1 - 10m
project_755 | Corporate | Land Referencing Services Area South | OJEU - Open |  | Awarded | Q4 2016 | Mott MacDonald | TBC | £8.2m | £1 - 10m
HS2_751 | Corporate | Built Environment Support Contract | Negotiated OJEU | N/A | Awarded | Q3 2017 | Lot A: Ove Arup International -Rob Leslie-Carter (rail@arup.com) Lot B: Atkins Global | https://www.contractsfinder.service.gov.uk/Notice/d3be68f7-21d2-4079-a58e-1ab4cbca1139?p=@T0=NjJNT08=UFQxUlRRP | £8.0m | £1 - 10m
2158 | Corporate | Provision of Support & Advice for HS2 Ltd’s Efficiency Challenge Programme (ECP) | Further Competition | CCS Management Consultancy 2 Framework | ITT in evaluation | Q1 2021 | TBC | N/A | £8m | £1 - 10m
1740 | Corporate | Print Production and Logistics Management Services | Further Competition | CCS RM3785: Managed Print & Digital Solutions | ITT in evaluation | Q4 2020 | TBC | TBC | £7.8m | £1 - 10m
HS2_1795 | Corporate | Travel and Venue Services | Further Competition (Framework Agreement Call-Offs > £50k) | CCS RM6016 Public Sector Travel and Venue Solutions | Awarded | Q3 2019 | Corporate Travel Management (North) Limited | TBC | £7.6m | £1 - 10m
project_756 | Corporate | Land Referencing Services Area Central | OJEU - Open |  | Awarded | Q4 2016 | Mouchel | TBC | £7.5m | £1 - 10m
1773 | Corporate | Estimating & Cost Management Services |  |  | Awarded | Q3 2019 | AECOM | TBC | £6.2m | £1 - 10m
project_755 | Corporate | Land Referencing Services Area North | OJEU - Open |  | Awarded | Q4 2016 | TerraQuest | TBC | £6.1m | £1 - 10m
HS2_1462 | Corporate | Document Control Service | Open OJEU | N/A | Awarded | Q2 2018 | Infocloud and MDE Consulting | https://ted.europa.eu/udl?uri=TED:NOTICE:365775-2018:TEXT:EN:HTML | £5m | £1 - 10m
2024 | Corporate | Euston OSD Development Consultant | Further Competition | CCS Estates Professional Services Framework | Awarded | Q3 2020 | Lot 1: Development Consultant - CBRE Ltd Lot 2: Town Planning - CBRE Ltd |  | £5m | £1 - 10m
Phase One: Ref#2152 | Construction | Phase One: Plant Material |  | N/A | Awarded | Q4 2016 | W Crowder & Sons Ltd - HS2@crowders.co.uk | http://ted.europa.eu/udl?uri=TED:NOTICE:98607-2016:TEXT:EN:HTML&src=0#. | £5-9m | £1 - 10m
WP1 | Corporate | Acquisitions and Advice - Manchester Leg | Further Competition | N/A | Awarded | Q3 2017 | Lambert Smith Hampton | TBC | £5.8m | £1 - 10m
project_539 | Corporate | Property and Planning Legal Services | Further Competition | N/A | Awarded | Q3 2016 | DLA Piper UK LLP | TBC | £5.5m | £1 - 10m
1771 | Corporate | Commercial Management Services for EWC and MWCC |  |  | Awarded | Q3 2019 | Turner & Townsend |  | £5.4m | £1 - 10m
HS2_1435 | Corporate | HS2 Helpdesk and Enquiries Centre | Further Competition (Framework Agreement Call-Offs > £50k) | CCS Network Services Lot 2 | Awarded | Q1 2019 | Sitel UK Ltd | https://www.contractsfinder.service.gov.uk/Notice/81dfc66f-49c1-447d-acc0-f9aeb9192557 | £4m | £1 - 10m
HS2 _TBC | Corporate | Route-wide Engagement Activities | Further Competition (Framework Agreement Call-Offs > £50k) | CCS Corporate Communications RM3796 - Lot 2 | Awarded | Q3 2018 | Glasgows Limited Contact: Tim Lowell e: timl@glasgows.co.uk | https://www.contractsfinder.service.gov.uk/Notice/5d56189c-f8cf-4bdd-8d80-d735e09f7c57?p=@=UFQxUlRRPT0=NjJNT08 | £4m | £1 - 10m
HS2_1183 | Corporate | Railway Systems Procurement Support | Direct Award under Framework | SCAPE BECS Framework | Awarded | Q2 2017 | Perfect Circle JV Ltd | https://www.contractsfinder.service.gov.uk/Notice/19e373da-74b8-4bfb-a9c0-93a4efafdd02?p=@T0=NjJNT08=UFQxUlRRP | £4.9m | £1 - 10m
| Corporate | Microsoft reseller for Azure Cloud services |  |  | Awarded | Q3 2017 | Trustmarque Solutions Limited |  | £4.6m | £1 - 10m
project_1840 | Corporate | BL2 Assurance for Phase 2a and 2b |  | N/A | Awarded | Q3 2017 | Pricewaterhouse Cooper Ltd | TBC | £3m | £1 - 10m
HS2_1287 | Corporate | Environment and Town Planning Support Services | Further Competition (Framework Agreement Call-Offs > £50k) | CCS Full Design And Project Management RM3741 | Awarded | Q1 2018 | Atkins Ltd (paul.white@atkinsglobal.com) | https://www.contractsfinder.service.gov.uk/Notice/7b02ba48-fe68-4153-9aa8-7aa07bc26175 | £3m | £1 - 10m
1919 | Corporate | Design Panel Secretariat Support | OJEU - Negotiated | N/A | Awarded | Q3 2020 | Frame Projects |  | £3.9m | £1 - 10m
HS2_528 | Corporate | Insurance Brokering Services | Negotiated OJEU | N/A | Awarded | Q3 2016 | JLT Specialty Ltd: Andrew_Birt@jltgroup.com | https://ted.europa.eu/TED/notice/udl?uri=TED:NOTICE:328584-2016:TEXT:EN:HTML | £3.7m | £1 - 10m
| Corporate | Land & Property Development Programme – Tranche 3 | Direct Award | N/A | Awarded | Q1 2019 | Ernst & Young LLP | TBC | £3.3m | £1 - 10m
project_540 | Corporate | Transport Model Development | Further Competition | N/A | Awarded | Q2 2016 | Systra Ltd | TBC | £3.2m | £1 - 10m
project_541 | Corporate | Transport Model Analysis | Further Competition | N/A | Awarded | Q2 2016 | Mott MacDonald | TBC | £2.8m | £1 - 10m
1872 | Corporate | Discretionary Schemes Valuation Services | OJEU - Negotiated | N/A | ITT in evaluation | Q1 2021 | TBC | TBC | £2.8m | £1 - 10m
1906 | Corporate | Health Exposure Monitoring (HEM) Solution | Further Competition | CCS Data and Applications | Awarded | Q3 2020 | Bramble Hub | TBC | £2.6m | £1 - 10m
| Corporate | CMS - Planning and Development of Rail Systems, Utilities and On-Network Work Packages |  | N/A | Awarded | Q3 2017 | Corderoy | TBC | £2.5m | £1 - 10m
HS2 Project_849 | Corporate | Events Delivery Partner | Further Competition (Framework Agreement Call-Offs > £50k) | CCS Framework Agreement RM1049 | Awarded | Q1 2017 | Bray Leino Ltd ncrossland@brayleino.co.uk | https://www.contractsfinder.service.gov.uk/Notice/e94a56ec-12db-4204-a4c6-af1f24f5f21c?p=@RPT0=NjJNT08=UFQxUlR | £2.4m | £1 - 10m
project_1138 | Corporate | Training Services | Further Competition | N/A | Awarded | Q3 2017 | Premier Partnerships | TBC | £4m | £1 - 10m
Project_1506 | Corporate | Supply Chain Management Services | Direct Award | N/A | Awarded | Q2 2020 | Gardiner and Theobald | TBC | £1.8m | £1 - 10m
project_661 | Corporate | Candidate Selection and Assess Service | Further Competition |  | Awarded | Q2 2016 | Penna PLC | TBC | £1.8m | £1 - 10m
project_1278 | Corporate | Euston OSD/MDP Procurement Legal Support | Direct Award | N/A | Awarded | Q3 2017 | Eversheds LLP | TBC | £1.6m | £1 - 10m
project_1509 | Corporate | Oracle Support - IBM |  | N/A | Awarded | Q3 2018 | IBM UK Ltd | TBC | £1.6m | £1 - 10m
1943 | Corporate | Corporate Finance and Rolling Stock Financial Advisory Services | Further Competition | CCS Management Consultancy Framework | Awarded | Q3 2020 | KPMG LLP | TBC | £1.5m | £1 - 10m
project_922 | Corporate | Grant Management Body | £50k to OJEU Threshold | N/A | Awarded | Q4 2016 | Groundwork's Ltd | TBC | £1.4m | £1 - 10m
2018 | Corporate | Unified Comms & Telephony Hardware | Further Competition | CCS Technology Products & Associated Services | Awarded | Q2 2020 | ComputaCenter UK Limited | TBC | £1.4m | £1 - 10m
1822 | Corporate | Insights Programme | Further Competition | CCS Research Marketplace DPS | Awarded | Q3 2020 | Market and Opinion Research International Ltd | TBC | £1.3m | £1 - 10m
| Corporate | Euston Over-Site Development Advisory | Further Competition | N/A | Awarded | Q4 2018 | Deloitte LLP | TBC | £1.2m | £1 - 10m
1562 | Corporate | Independent Review and Assurance Panel |  | N/A | Awarded | Q3 2018 | The Institution of Civil Engineers (ICE) | TBC | £1.2m | £1 - 10m
| Corporate | Recruitment advertising | Further Competition |  | Awarded | Q3 2015 | TMP | TBC | £1.2m | £1 - 10m
1838 | Corporate | Commercial Management Services for the Planning and Development of Station Procurement Activities |  |  | Awarded | Q3 2019 | Turner & Townsend | TBC | £1.1m | £1 - 10m
HSE605 | Corporate | Enhanced Policing Services Agreement for the provision of a Liaison officer and other Services |  |  | Awarded | Q4 2016 | British Transport Police Authority | TBC | £1.1m | £1 - 10m
2159 | Corporate | Stations - Customer Analysis | Further Competition | CCS Market Research DPS | ITT | Q1 2021 | TBC | N/A | £80k | £0 - £1m
2144 | Corporate | Independent Plant Material Assessor | Further Competition | ESPO Consultancy Services Framework | ITT | Q1 2021 | TBC | N/A | £160k | £0 - £1m

## Notes
Categories | Status | Value range
Construction | Not started | £0 - 1m
Corporate | PQQ | £1 - 10m
Rolling Stock | PQQ in evaluation | £10 - 50m
Railway Systems | ITT | £50 - 100m
| ITT in evaluation | £100 - 250m
| Awarded | £250 - 500m
| TBC | £500m - £3bn