## Procurement Timeline
| JV Contractor Procurement Pipeline | Indirect contract opportunities We publish details of current and forthcoming subcontract procurements to be undertaken by our Joint Venture (JV) contractors, to provide early visibility of opportunities to the market. Please see www.competefor.com/hs2 for more details or get in touch directly with the relevant JV, using the contact details provided below: - BBV: supplychainmanagement@balfourbeattyvinci.com (e-sourcing platform: Jaggaer) - SCS: supplychain@scsrailways.co.uk (e-sourcing platform: SourceDogg) - EKFB: supplychainenquiries@ekfb.com (e-sourcing platform: Market Dojo) - Align: scmteam@alignjv.com (e-sourcing platform: Wax Digital) - BBVS: supplychain@bbvsjv.com (e-sourcing platform: Jaggaer) - MD (Euston): procurement@macedragados.com - MD (Curzon): bcz.procurement@macedragados.com
Last Updated: Q1 2025
Tier 1 Contractor | Tier 1 Contract to HS2 | Tier 2 Sub-Contract Package | Estimated Procurement Start Date | Estimated Contract Value Range
|  |  | (month or quarter) | (less than £1m, £1m - £5m, £5m - £10m, £10m - £50m, and £50m+)
ALIGN JV (Bouygues, VolkerFitzpatrick, Sir Robert McAlpine) | Main Works Civils Contract (MWCC): C1 Area Central | Permanent Drainage | Q2 2025 | £1m - £5m
ALIGN JV (Bouygues, VolkerFitzpatrick, Sir Robert McAlpine) | Main Works Civils Contract (MWCC): C1 Area Central | Soft Landscaping | Q2 2025 | £1m - £5m
ALIGN JV (Bouygues, VolkerFitzpatrick, Sir Robert McAlpine) | Main Works Civils Contract (MWCC): C1 Area Central | External Works – phase 2 (TBC) | Q2 2025 | £1m - £5m
ALIGN JV (Bouygues, VolkerFitzpatrick, Sir Robert McAlpine) | Main Works Civils Contract (MWCC): C1 Area Central | Permanent Drainage | Q2 2025 | £1m - £5m
ALIGN JV (Bouygues, VolkerFitzpatrick, Sir Robert McAlpine) | Main Works Civils Contract (MWCC): C1 Area Central | Specialist Hard-landscaping packages | Q2 2025 | £1m - £5m
ALIGN JV (Bouygues, VolkerFitzpatrick, Sir Robert McAlpine) | Main Works Civils Contract (MWCC): C1 Area Central | Roads and Surfacing | Q2 2025 | £1m - £5m
ALIGN JV (Bouygues, VolkerFitzpatrick, Sir Robert McAlpine) | Main Works Civils Contract (MWCC): C1 Area Central | Leather Lane (procurement model to be confirmed) | Q2 2025 | £1m - £5m
ALIGN JV (Bouygues, VolkerFitzpatrick, Sir Robert McAlpine) | Main Works Civils Contract (MWCC): C1 Area Central | Specialist Seed Supply | Q3 2025 | less than £1m
ALIGN JV (Bouygues, VolkerFitzpatrick, Sir Robert McAlpine) | Main Works Civils Contract (MWCC): C1 Area Central | GMI/2 and Leatherlane - Vehicle Restraint System | Q3 2025 | less than £1m
ALIGN JV (Bouygues, VolkerFitzpatrick, Sir Robert McAlpine) | Main Works Civils Contract (MWCC): C1 Area Central | GMI/2 & GMI/12 Lineside GRS Stairs | Q3 2025 | less than £1m
ALIGN JV (Bouygues, VolkerFitzpatrick, Sir Robert McAlpine) | Main Works Civils Contract (MWCC): C1 Area Central | Permanent Fencing | Q3 2025 | less than £1m
ALIGN JV (Bouygues, VolkerFitzpatrick, Sir Robert McAlpine) | Main Works Civils Contract (MWCC): C1 Area Central | Soil Stabilisation | Q2 2025 | less than £1m
ALIGN JV (Bouygues, VolkerFitzpatrick, Sir Robert McAlpine) | Main Works Civils Contract (MWCC): C1 Area Central | Amersham Highways Drainage | Q2 2025 | less than £1m
ALIGN JV (Bouygues, VolkerFitzpatrick, Sir Robert McAlpine) | Main Works Civils Contract (MWCC): C1 Area Central | River Colne Bridge | Q2 2025 | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Civils Package Stonebridge Island - Including WP5 Area C Drainage | Q2 2025 | £10m - £50m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Drainge SL7 wide (Mainline Package) | Q2 2025 | £10m - £50m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | FRC Package 5 | Q2 2025 | £10m - £50m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | FRC Package 4.2 | Q3 2025 | £10m - £50m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | M6 Junction 4 - Multi Discipline Civils | Q3 2025 | £10m - £50m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Track Drainage - Package 2 (incl Noise Barrier Install) | TBC | £10m - £50m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Track Drainage & Noise Barrier Install - Stoneleigh & North | TBC | £10m - £50m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Natural Capital Professional Services | TBC | £10m - £50m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Remaining SL5s Landscaping & Seeding | Q2 2025 | £5m - £10m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | FRC - S1 (Package B) - Shadow Brook Bridleway Underbridge | Q2 2025 | £5m - £10m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Track Drainage - Package 3 | TBC | £5m - £10m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Landscaping | TBC | £5m - £10m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Misc Roads/Footpaths & Culvert Install (Procurement Strategy TBC) | TBC | £5m - £10m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | PSV - Cable trough covers & stairs | Q2 2025 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Supply and installation of auxiliary steel works (hand rails, work platform, steel staircases, etc.) | Q2 2025 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Stainless Steel Reinforcement (Cut and Bend) | Q2 2025 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | External dumps | Q2 2025 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | WP5 Area C Street Lighting, Signs and Electricals | Q2 2025 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Parapets installation | Q2 2025 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Trace Drainage - Coleshill No. 2 | Q2 2025 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Trace Drainage - Bickenhill Embankment | Q2 2025 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | FRC - S7 - 3 Structures (Area C) | Q2 2025 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Trace Drainage - Shadow Brook | Q2 2025 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Shotcrete Wall | Q2 2025 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Trace Drainage - Hollywell Brook | Q3 2025 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Trace Drainage - Coleshill Underbridge | Q3 2025 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Trace Drainage - Coleshill No. 1 | Q3 2025 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Trace Drainage - M42 Box | Q4 2025 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Trace Drainage - 154-L2 & 155-L3 - Diddington Embankment & Cutting | Q4 2025 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Trace Drainage - 160-L2 & L4 - Coleshill Embankments | Q1 2026 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Trace Permanent Fencing | Q1 2026 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Drainage Supply Only | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Drainage (Delayed) | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Lichfield diversion (Highway diversion) | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Steel Footbridge - K29 | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Dalehouse Lane - Reinforced Earth Wall Installation | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Roadworks Package 3 - Crackley Lane | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | LIWSP - LRC - Access & MEP Buildings External Works | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | LIWNP - Welsh Road Access & MEP Buildings External Works | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Roadworks Package 4 - Waste Lane | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | FRC7 (Carol Green run-on slab & other works) | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Noise Barrier Pilling - 2025 Requirements | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Remaining Technical Backfill Install (Procurement Strategy TBC) | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Balancing Pond Lining | Q2 2025 | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Culvert Installation | Q2 2025 | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Parapets (Parapet for Non HS2 Structures) | Q2 2025 | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Electrical - Street lighting for highway and box structures | Q2 2025 | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | PSV - Finishing works formworks | Q2 2025 | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Permanent Fencing for KD11 | Q2 2025 | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Supply and installation of auxiliary steel works (hand rails, work platform, steel staircases, etc.) | Q2 2025 | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Pipe Jacking - Packington Culvert | Q2 2025 | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | East Way & Service Road - VRS | Q2 2025 | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Precast Cladding for Chester Rd (Station Exit) Overbridge | Q2 2025 | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | SL5s - M6 Mechanical Expansion Joints - (Supply Only) | Q2 2025 | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | WP5 Area C VRS | Q2 2025 | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Trace Drainage - M6 Viaduct | Q4 2025 | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Pedestrian Guardrail | Q4 2025 | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Dalehouse Lane Reinforced Earth Wall - Supply Only | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Security CCTV Management | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Rootlock (Landscaping retaining wall construction) | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Print & Reprographic services | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | FRC Pkg F (4no.of 6 Remaining assets) | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Installation of Precast Arches | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | LIWSP - A425 Reinstatement | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | LIWSP & NP - UTX | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Mercote Hall Lane & M218 Bridleway Roadworks | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Berkswell Sidings - Access Roads, Drainage & Ducting | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | SPMT Operators | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Demolition of A46 Guide Slab | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Streetlighting | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Installation of Lineside Drainage 7.2 | Q3 2025 | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | MLN- Scaffolding | Q1 2026 | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | BROT IS - Cable Adit Frames | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | BROT IS - External works | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Installation of Parapets and Deck finishing works | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | BROT East/West and IS Tarmac | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | BROT East/West/IS Landscaping | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | BROT East Groundworks | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | BROT East/West and IS permanent security fence | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | BROT West Groundworks | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | BROT Temporary ventilation for Civil work phase | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | BROT - Permanent security Fencing | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Water Abstraction | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | A446 Highway permanent works | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Lime Equipment | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Curborough Brook Diversion | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Track Drainage | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Handrails | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Precast Robust Kerbs | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Shotcrete | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Wood End Mooring Demolition | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | I&M Mainline North | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Viaduct Underground Drainage CZN | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Saltley Drainage materials | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | WWH Drainage DD1b and DD1c | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | WWH A47 Abutment FRC works | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Sublot wide expansion joints / Bridge joints | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Install of Abutment Staircase FRC Structures | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Supply and Install of a Temporary Footbridge | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Metalwork - Doors, Metal Guardrails | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Freightliner Bellmouth | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Drainage DD1c | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Top soil requirments | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Pre Cast Box Culverts Retained fill underpass - Supply | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Potential Attentuation tank Non Pre cast | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Sheetpiling (Area 9) VFM | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Duddeston junction viaduct attenuation Tank | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Aggregate Day Rate Tippers | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Surveys | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | River Rea Seal to Existing Calvert | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Highways - furniture, lights, signs | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Installation of Noise Barriers | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Highways Signage | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | SL8.1 Civils works | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Asphaltic Plug Joints | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Stoneleigh Retaining Wall - Sheet Piling | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Mechanical Plug joints | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Temporary & Permanent Sheet Piling 2.0 | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Temporary & Permanent Sheet Piling phase 2 | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | BROT East&West Portals, Intermediate Shaft: Road Markings | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Workforce Management System | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Abutment Staircase - FRC Structures | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Resident Driveways | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Heavy Lifting Crane- Harveys Rough | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Water Course Diversions | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Footbridges - Structural Steelwork | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Hydroseeding | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | MLN Temporary Bridges | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Welding Inspectors | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | DE Vegetation - Trackside & site wide | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Curzon 1 Architectural Finishing’s | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Duddeston Viaduct Architectural Finishing’s | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | BROT - Cross Passages Temporary Steel Frames | TBC | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | Temporary Weatherproofing Structures | Q2 2025 | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | Final Builders Clean before final handover | Q1 2026 | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | Urban Realm (Landscaping, Roads & Pavements) | Q2 2025 | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | HS2 Granazzo Flooring | Q2 2025 | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | Toilet Fit-Out | Q2 2025 | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | Painting & Decorating | Q2 2025 | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | Furnishings, fittings & equipment | Q2 2025 | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | HS2 Station Platform Flooring | Q2 2025 | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | SAB Flooring | Q2 2025 | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | Signage & Wayshowing | Q3 2025 | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | HS2, SAB & GWML Internal Art Cladding | Q3 2025 | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | Bird Deterrent | Q4 2025 | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | SAB Cladding | Q4 2025 | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | Builder's Clean | Q4 2025 | TBC
Eiffage Kier Ferrovial Bam (EKFB) | MWCC C2 C3 | Noise Barrier Steel Columns | Q2 2025 | £10m - £50m
Eiffage Kier Ferrovial Bam (EKFB) | MWCC C2 C3 | Boundary Fencing - multiple packages | Q2 2025 | £1m - 5m, £5m - 10m, £10m - £50m
Eiffage Kier Ferrovial Bam (EKFB) | MWCC C2 C3 | Security Fencing Install - multiple packages | Q2 2025 | £1m - 5m, £5m - 10m, £10m - £50m
Eiffage Kier Ferrovial Bam (EKFB) | MWCC C2 C3 | Security Fencing supply - multiple packages | Q2 2025 | £1m - 5m, £5m - 10m, £10m - £50m
Eiffage Kier Ferrovial Bam (EKFB) | MWCC C2 C3 | Drainage Materials - Plastic and Poncrete products Framework Orders | Q2 2025 | £1m - 5m, £5m - 10m, £10m - £50m
Eiffage Kier Ferrovial Bam (EKFB) | MWCC C2 C3 | Trackside Drainage - Routewide Packages across EKFB Projects | Q3 2025 | £5m - £10m
Eiffage Kier Ferrovial Bam (EKFB) | MWCC C2 C3 | Noise Barrier Install - multiple packages | Q4 2025 | £5m - £10m
Eiffage Kier Ferrovial Bam (EKFB) | MWCC C2 C3 | Access Steps and Stairs | Q2 2025 | Less than £1m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Façade Systems - Curtain Walling and Glazing | Q2 2025 | £10m - £50m
Mace Dragados (MD) | Curzon Street Station Construction Partner | RC Main Works Superstructure | Q2 2025 | £10m - £50m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Hard Landscaping | Q1 2026 | £10m - £50m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Structural Steelwork | Q2 2025 | £10m - £50m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Standing Seam Roof | Q2 2025 | £5m - £10m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Facade - Structural Glazing (East & West Gable End) | Q2 2025 | £5m - £10m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Architectural Metalwork | Q1 2026 | £5m - £10m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Brickwork | Q4 2025 | £5m - £10m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Fit out (numerous packages) | Q4 2025 | £5m - £10m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Vehicle Barriers | Q2 2026 | £1m - £5m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Facade Systems - PC & GRC Façade Panels | Q2 2025 | £1m - £5m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Temporary Electrics | Q2 2025 | £1m - £5m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Soft Landscaping | Q1 2026 | £1m - £5m
Mace Dragados (MD) | Curzon Street Station Construction Partner | External Lighting to urban realm | Q3 2026 | £1m - £5m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Scaffolding | Q2 2025 | £1m - £5m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Mansafe System | Q1 2026 | £1m - £5m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Firestopping | Q3 2026 | £1m - £5m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Dock Levellers | Q2 2026 | TBC
Mace Dragados (MD) | Curzon Street Station Construction Partner | Wheelchair/Scissor Lifts | Q2 2025 | TBC
Mace Dragados (MD) | Euston Station Construction Partner | Traction Substation Façade Cladding | Q2 2026 | £5m - £10m
Mace Dragados (MD) | Euston Station Construction Partner | Traction Substation Demolition | Q2 2025 | £1m - £5m
Mace Dragados (MD) | Euston Station Construction Partner | Materials by Rail Operator and Train Provision | Q2 2025 | £1m - £5m
Mace Dragados (MD) | Euston Station Construction Partner | Materials by Rail Muck Away Disposal Sites | Q2 2025 | £1m - £5m
Mace Dragados (MD) | Euston Station Construction Partner | Ground Anchors | Q2 2025 | £1m - £5m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Waterproofing - Middle & South | Q2 2025 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Euston Assets - Metalwork Task Order | Q1 2026 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Metal Doors & Ironmongery (Standard) - GRVS & WRP | Q1 2026 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Euston - Headhouse Roofing | Q1 2027 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | HRB - Expansion Joints (South) | Q1 2027 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Rail Corridor Mitigations | Q1 2027 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Temporary Gantry Cranes (ESB) | Q1 2027 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Headhouse Frame (North) | Q1 2029 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Metal Doors and Ironmongery (Standard) Supply and Install –– ARVS and CRVS | Q1 2029 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Euston Scissor Box Portal Headhouse - Cladding | Q1 2031 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Area East Headhouses - Floor Finishes | Q1 2032 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Area East Headhouses - Wayfinding and Signage | Q1 2032 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Equipment - Crane - Tower (West) | Q2 2025 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Operated Plant - Mobile Concrete Pumps - (Framework Renewal) | Q2 2025 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Propping and Temporary Works (HRB) | Q2 2025 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Precast Brick Slip Clad Wall (circa 200m along WR Portal) | Q2 2026 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Sprayed Concrete (South/Middle) | Q2 2026 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | GTB - Expansion Joints (South) | Q2 2027 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Track Drainage Survey's | Q2 2027 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Fencing - Permanent | Q2 2030 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Landscaping (South/Middle) | Q2 2032 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Bridge Steelwork and Bearings (South/Middle) | Q3 2025 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Hard Landscaping - WRP (inc. minor civils) | Q3 2025 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | PPE (Framework Renewal) | Q3 2025 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Soft Landscaping (WRP) | Q3 2025 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Traffic Management Phasing | Q3 2025 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Brickwork and Blockwork Detailed Design - Adelaide road | Q3 2026 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Cladding Detailed Design - Adelaide Road | Q3 2026 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Concrete Lab (VHA) | Q3 2026 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Metal Doors and Ironmongery (Standard) Detailed design – ARVS and CRVS | Q3 2026 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Roadworks - HRB & GTB Finishing works | Q3 2026 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Heritage Works (Asset Protection) | Q3 2027 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Area East Headhouses - Internal Walls (blockwork) | Q3 2031 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Area East Headhouses - Steelwork | Q3 2031 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Corrosion Protection & Anti-Graffiti Coatings | Q3 2031 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Hoarding for Zone 5 & ETRC | Q4 2025 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Phase 1 Utilities Removal | Q4 2025 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Rail Freight Operating Services (Euston Tunnels Extension) | Q4 2025 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Terminal Operations (Euston Tunnels Extension) | Q4 2025 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Track Inspection and Maintenance (Euston Tunnels Extension) | Q4 2025 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Metalwork Task Order - Canterbury and Adelaide | Q4 2026 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Brickwork and Blockwork Supply and Install - Adelaide road | Q4 2027 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Cladding Supply and Installation - Adelaide Road | Q4 2027 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Precast - ESB Roof Panels (South) | Q4 2027 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Shot Blasting (Liner Walls) | Q4 2027 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Tunnel Secondary Lining Shuttering (North) | Q4 2028 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Tunnel Water Proofing (North) | Q4 2028 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Area East Headhouses - Roof Finishes | Q4 2031 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Euston Cavern Shaft Headhouse - Cladding (North) | Q4 2031 | TBC

## Sheet1
£50m+ | Q1 2024
£10m - £50m | Q2 2024
£5m - £10m | Q3 2024
£1m - £5m | Q4 2024
£1m - £5m, £5m - £10m, £10 - £50m | Q1 2025
Less than £1m | Q2 2025
TBC | Q3 2025
Q4 2025
Q1 2026
Q2 2026
Q3 2026
Q4 2026
Q1 2027
Q2 2027
Q3 2027
Q4 2027
TBC