## Procurement Timeline
| JV Contractor Procurement Pipeline | Indirect contract opportunities We publish details of current and forthcoming subcontract procurements to be undertaken by our Joint Venture (JV) contractors, to provide early visibility of opportunities to the market. Please see www.competefor.com/hs2 for more details or get in touch directly with the relevant JV, using the contact details provided below: - BBV: supplychainmanagement@balfourbeattyvinci.com (e-sourcing platform: Jaggaer) - SCS: supplychain@scsrailways.co.uk (e-sourcing platform: SourceDogg) - EKFB: supplychainenquiries@ekfb.com (e-sourcing platform: Market Dojo) - Align: scmteam@alignjv.com (e-sourcing platform: Wax Digital) - BBVS: supplychain@bbvsjv.com (e-sourcing platform: Jaggaer) - MD (Euston): procurement@macedragados.com - MD (Curzon): bcz.procurement@macedragados.com
Last Updated: Q4 2025
Tier 1 Contractor | Tier 1 Contract to HS2 | Tier 2 Sub-Contract Package | Estimated Procurement Start Date | Estimated Contract Value Range
|  |  | (month or quarter) | (less than £1m, £1m - £5m, £5m - £10m, £10m - £50m, and £50m+)
ALIGN JV (Bouygues, VolkerFitzpatrick, Sir Robert McAlpine) | Main Works Civils Contract (MWCC): C1 Area Central - SHC | 47 No. Boreholes | Q2 2026 | £1m - £5m
ALIGN JV (Bouygues, VolkerFitzpatrick, Sir Robert McAlpine) | Main Works Civils Contract (MWCC): C1 Area Central - SHC | White Lining | Q3 2026 | Less than £1m
ALIGN JV (Bouygues, VolkerFitzpatrick, Sir Robert McAlpine) | Main Works Civils Contract (MWCC): C1 Area Central - SHC | Permanent Signage | Q3 2026 | Less than £1m
ALIGN JV (Bouygues, VolkerFitzpatrick, Sir Robert McAlpine) | Main Works Civils Contract (MWCC): C1 Area Central - SHC | Surfacing Exclusion & Kerbs | Q2 2026 | Less than £1m
ALIGN JV (Bouygues, VolkerFitzpatrick, Sir Robert McAlpine) | Main Works Civils Contract (MWCC): C1 Area Central - SHC | Earthing & Bonding | Q2 2026 | Less than £1m
ALIGN JV (Bouygues, VolkerFitzpatrick, Sir Robert McAlpine) | Main Works Civils Contract (MWCC): C1 Area Central - SHC | Ancillary (Kerbs & Drainage Kerbs, Bollards) | Q3 2026 | Less than £1m
ALIGN JV (Bouygues, VolkerFitzpatrick, Sir Robert McAlpine) | Main Works Civils Contract (MWCC): C1 Area Central - SHC | Vehicle Restraint System | Q2 2026 | Less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | M6 Junction 4 - Multi Discipline Civils | Q4 2026 | £10m - £50m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Civils Package Stonebridge Island - Including WP5 Area C Drainage | Q3 2026 | £10m - £50m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Track Drainage (incl NB Pilecap) - Package 2 | TBC | £10m - £50m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Natural Capital Professional Services | TBC | £10m - £50m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | New Ecological Mitigation Sites (Landscaping) | TBC | £10m - £50m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Central East (SL5s & Delta) Landscaping & Seeding Package | Q3 2026 | £5m - £10m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Remaining Highways Drainage Packages (5no Assets) | Q2 2026 | £5m - £10m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Non-Hazardous Skip Waste Management (Excl. Mixed Metals) | TBC | £5m - £10m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | FRC - S1 (Package B) - Shadow Brook Bridleway Underbridge | Q1 2026 | £5m - £10m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Track Drainage (incl NB Pilecap) - Package 3 | TBC | £5m - £10m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Landscaping - 2026 Requirements | TBC | £5m - £10m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Supply & Installation of Permanent Fencing (Security & Boundary) | TBC | £5m - £10m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Track & Highways Drainage - Package 2 | TBC | £5m - £10m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | FRC - S7 - 3 Structures (Area C) | Q2 2026 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | WP5 Area C Street Lighting, Signs and Electricals | Q2 2026 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Trace Permanent Fencing | Q1 2026 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Electrical - Street lighting for highway and box structures | Q2 2026 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | A446 Highway permanent works | Q3 2026 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Lichfield diversion (Highway diversion) | Q3 2026 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Stainless Steel Reinforcement (Cut and Bend) | Q1 2026 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Secondary asset staircases | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Installation of Culverts - Ash Beds, Coventry Road & Leicester Lane | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | 2026 - Muck Movement Package 1 | Q1 2026 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | 2026 - Muck Movement Package 2 | Q1 2026 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | 2027 - Muck Movement Package 1 | Q4 2026 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | 2027 - Muck Movement Package 2 | Q4 2026 | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Technical Backfill Package 2 (BG Tunnel U-box, M186, W168, South Portal) | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | W164 & W165 Roadworks | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Crackley ATFS - Civils Scope | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Installation of Permanent Security Fencing | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Permanent Boundary Fencing | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Marsh Farm to M214 - Completion Works | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Marsh Farm Civils Works - Phase 3 (Marsh Lane Culvert, Remaining Brook Realignment) | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Track Drainage (incl NB Pilecap) - Package 4 | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Supply of Precast UTX Chambers | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | FRC8 - BCV & RBV Retaining Wall (FRC Works) | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Slipform Concrete Works - Patrick Embankment | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Staircases | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Burton Green - Noise Barrier Installation | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | New Ecological Mitigation Sites (Landscaping) | TBC | £1m - £5m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Parapets (Parapet for Non HS2 Structures) | Q1 2026 | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Precast Cladding for Chester Rd (Station Exit) Overbridge | Q3 2026 | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Pipe Jacking - Packington Culvert | Q1 2026 | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Balancing Pond Lining | Q1 2026 | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | WP5 Area C VRS | Q2 2026 | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Mixed Metals Recycling | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Waste Water Management | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | East Way & Service Road - VRS | Q2 2026 | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Pedestrian Guardrail | Q3 2026 | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | M6 Mechanical Expansion Joints - (Supply Only) | Q1 2026 | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Footpath Realignments | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Slip Form & Concrete Barrier | Q2 2026 | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Tipper Trucks - 2026 | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Bockenden Access Road &W168, M186 | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Demolition of Exisiting Culverts at A452 | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Demolition of Dalehouse Farm | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Remaining Roadworks for 2B1 Pumping Station | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | M214 to Balsall Common - Completion Works | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Shotcrete & Soil Nailing - Canley Brook Pumping Station | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Landscaping (Planting & Seeding) - Package 3 | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Supply of Precast UTX Chambers | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Tipper Trucks - 2027 | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Tipper Trucks - 2027 | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Kenilworth, Broadwells Permanent Pond & Broadwells Watercourse Diversion | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Marsh Farm - Temporary Junction | TBC | less than £1m
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | BROT IS - Cable Adit Frames | Q1 2026 | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | BROT East/West/IS Landscaping | Q2 2026 | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | BROT East/West and IS permanent security fence | Q2 2026 | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | BROT West Groundworks | Q2 2026 | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | BROT Temporary ventilation for Civil work phase | Q2 2026 | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | BROT - Permanent security Fencing | Q2 2026 | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Sublot wide expansion joints / Bridge joints | Q1 2026 | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Hazardous Waste | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Freightliner Bellmouth | Q2 2027 | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Pre Cast Box Culverts Retained fill underpass - Supply | Q3 2026 | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Potential Attentuation tank Non Pre cast | Q2 2027 | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Duddeston junction viaduct attenuation Tank | Q2 2026 | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | River Rea Seal to Existing Calvert | Q2 2026 | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Curzon 1 Architectural Finishing’s | Q1 2026 | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Duddeston Viaduct Architectural Finishing’s | Q2 2026 | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Bromford Tunnel Intermediate Shaft –Final Demobilisation and Site Clearance | Q3 2026 | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | Curzon Wharf Second Stage Remediation | Q1 2026 | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | "U" Shape Channel Covers - Precast | Q2 2026 | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | RMX Concrete | TBC | TBC
Balfour Beatty Vinci (BBV JV) | Main Works Civils Contract (MWCC): N1 & N2 Area North | SL1 - Bromford East Cross Passages - Door Formwork | TBC | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | SAB Flooring | Q2 2026 | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | Urban Realm (Landscaping, Roads & Pavements) | Q2 2026 | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | HS2 Granazzo Flooring | Q1 2028 | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | Toilet Fit-Out | Q3 2026 | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | Signage & Wayshowing | Q1 2027 | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | HS2, SAB & GWML Internal Art Cladding | Q2 2027 | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | Bird Deterrent | Q3 2026 | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | Final Builders Clean before final handover | Q4 2031 | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | Furnishings, fittings & equipment | Q2 2026 | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | SAB Cladding | Q4 2026 | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | Part 2 & 3 Bridges | Q2 2026 | TBC
Balfour Beatty Vinci Systra (BBVS) | Old Oak Common Station Construction Partner (S4) | Ticket Machines | Q2 2028 | TBC
Eiffage Kier Ferrovial Bam (EKFB) | MWCC C2 C3 | Post contract Data Archive | Q4 2026 | £5m - £10m
Eiffage Kier Ferrovial Bam (EKFB) | MWCC C2 C3 | Soil Remediation - Various packages | Q4 2026 | £5m - £10m
Eiffage Kier Ferrovial Bam (EKFB) | MWCC C2 C3 | Access Steps and Stairs Framework - GRP | Q2 2026 | £1m - £5m
Eiffage Kier Ferrovial Bam (EKFB) | MWCC C2 C3 | Drainage Materials - Concrete products Framework Orders | Q2 2026 | £1m - £5m
Eiffage Kier Ferrovial Bam (EKFB) | MWCC C2 C3 | I&M Structures Monitoring - Multiple packages | Q2 2026 | £1m - £5m
Eiffage Kier Ferrovial Bam (EKFB) | MWCC C2 C3 | Portal Tunnel building substructure Civils | Q3 2026 | £1m - £5m
Eiffage Kier Ferrovial Bam (EKFB) | MWCC C2 C3 | GT Channel Drainage | Q2 2026 | £1m - £5m
Eiffage Kier Ferrovial Bam (EKFB) | MWCC C2 C3 | Street lighting | Q2 2026 | Less than £1m
Eiffage Kier Ferrovial Bam (EKFB) | MWCC C2 C3 | PCC Dividing wall - Calvert | Q2 2026 | Less than £1m
Eiffage Kier Ferrovial Bam (EKFB) | MWCC C2 C3 | Weathered steel wall posts - Calvert | Q2 2026 | Less than £1m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Façade Systems - Curtain Walling and Glazing | Q4 2026 | £10m - £50m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Hard Landscaping | Q1 2027 | £10m - £50m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Standing Seam Roof | Q3 2026 | £5m - £10m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Facade - Structural Glazing (East & West Gable End) | Q4 2026 | £5m - £10m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Architectural Metalwork | Q3 2027 | £5m - £10m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Brickwork | Q2 2027 | £5m - £10m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Fit out (numerous packages) | Q2 2027 | £5m - £10m
Mace Dragados (MD) | Euston Station Construction Partner | Traction Substation Façade Cladding | Q2 2026 | £5m - £10m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Facade Systems - PC & GRC Façade Panels | Q3 2026 | £1m - £5m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Mansafe System | Q3 2026 | £1m - £5m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Soft Landscaping | Q2 2027 | £1m - £5m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Scaffolding | Q2 2026 | £1m - £5m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Firestopping | Q1 2028 | £1m - £5m
Mace Dragados (MD) | Curzon Street Station Construction Partner | External Lighting to urban realm | Q2 2027 | £1m - £5m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Dock Levellers | Q2 2027 | £1m - £5m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Wheelchair/Scissor Lifts | Q2 2027 | £1m - £5m
Mace Dragados (MD) | Curzon Street Station Construction Partner | Vehicle Barriers | Q2 2027 | £1m - £5m
Mace Dragados (MD) | Euston Station Construction Partner | Traction Substation Demolition | Q2 2026 | £1m - £5m
Mace Dragados (MD) | Euston Station Construction Partner | Ground Anchors | Q4 2026 | £1m - £5m
Mace Dragados (MD) | Euston Station Construction Partner | O & M Manuals | Q1 2026 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Adelaide and Canterbury FRC | Q3 2026 | £10m - £50m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Area East Headhouses - Roof Finishes | Q4 2031 | £1m - £5m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Area East Headhouses - Steelwork | Q3 2031 | £1m - £5m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Euston - Headhouse Roofing | Q1 2027 | £1m - £5m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Euston Tunnels - Invert and Walkways - Ready Mixed Concrete Supply | Q2 2026 | £1m - £5m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Euston Tunnels - Invert and Walkways Labour Supply | Q2 2026 | £1m - £5m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Fencing - Permanent | Q2 2030 | £1m - £5m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Landscaping (South/Middle) | Q2 2032 | £1m - £5m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | PPE (Framework Renewal) | Q1 2026 | £1m - £5m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Precast Brick Slip Clad Wall (circa 200m along WR Portal) | Q3 2026 | £1m - £5m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Propping and Temporary Works (HRB) | Q2 2026 | £1m - £5m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Sprayed Concrete (North) including Batching Plant | Q1 2027 | £1m - £5m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Sprayed Concrete (South/Middle) | Q2 2026 | £1m - £5m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Vehicle Turntable (Euston DU) | Q4 2026 | £1m - £5m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Area East Headhouses - Floor Finishes | Q1 2032 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Area East Headhouses - Internal Walls (blockwork) | Q3 2031 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Area East Headhouses - Wayfinding and Signage | Q1 2032 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Brickwork and Blockwork Detailed Design - Adelaide road | Q3 2026 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Brickwork and Blockwork Supply and Install - Adelaide road | Q4 2027 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Cladding Detailed Design - Adelaide Road | Q3 2026 | less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Cladding Supply and Installation - Adelaide Road | Q4 2027 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Concrete Lab (VHA) | Q3 2026 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Corrosion Protection & Anti-Graffiti Coatings | Q3 2031 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Euston Assets - Metalwork Task Order | Q1 2026 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Euston Cavern Shaft & Headhouse - HVAC Task Order | Q4 2027 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Euston Cavern Shaft & Headhouse - MEP Task Order | Q4 2027 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Euston Cavern Shaft Headhouse - Cladding (North) | Q4 2031 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Euston Cavern Shaft Steelwork (North) | Q1 2027 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Euston Portal Headhouse - HVAC Task Order | Q4 2027 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Euston Portal Headhouse - MEP Task Order | Q4 2027 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Headhouse Frame (North) | Q1 2029 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Heritage Works (Asset Protection) | Q3 2027 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Metal Doors and Ironmongery (Standard) Detailed design – ARVS and CRVS | Q3 2026 | less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Metal Doors and Ironmongery (Standard) Supply and Install –– ARVS and CRVS | Q1 2029 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Metalwork Task Order - Canterbury and Adelaide | Q4 2026 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Precast - ESB Roof Panels (South) | Q4 2027 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Shot Blasting (Liner Walls) | Q4 2027 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Temporary Accomodation - Cavern Shaft Welfare (North) | Q3 2026 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Temporary Gantry Cranes (ESB) | Q1 2027 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Temporary Plunge Columns Steel Frame | Q4 2026 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Track Drainage Survey's | Q2 2027 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Waterproofing - Middle & South | Q1 2026 | Less than £1m
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Tunnel Secondary Lining Shuttering (North) | Q4 2028 | TBC
Skanska Costain Strabag (SCS) | Main Works Civils Contract (MWCC): S1 & S2 Area South | Tunnel Water Proofing (North) | Q4 2028 | TBC

## Sheet1 (hidden)
£50m+ | Q1 2024
£10m - £50m | Q2 2024
£5m - £10m | Q3 2024
£1m - £5m | Q4 2024
£1m - £5m, £5m - £10m, £10 - £50m | Q1 2025
Less than £1m | Q2 2025
TBC | Q3 2025
Q4 2025
Q1 2026
Q2 2026
Q3 2026
Q4 2026
Q1 2027
Q2 2027
Q3 2027
Q4 2027
TBC